## PMMRPT001_201
Department of Water Supply & Sanitation, Punjab
Website: www.pbdwss.gov.in
Performa Report 1.2
Five Year Action Plan: Part - 2
[47 empty] | As on : | [5 empty] | 08-Oct-2017
Sr. No. |  | Village Name |  | Scheme Name | Present Status of Water Supply | [10 empty] | Present Status of Water Supply in 2017 | [29 empty] | Details of Distribution pipe line (In KM) | [8 empty] | % age of functional Distribution network as in 2017.
[16 empty] | In case of T/well based schemes details of latest tubewell drilled at site | [8 empty] | In case of Canal based wss details of structures | [10 empty] | Details of OHSR's
[5 empty] | Water Supply Scheme under which habitaitons has been covered | Source of WSS | Type of scheme | WSS MIS ID. | Original Date of commissioning of WSS | Programme under which WSS was commissioned | Service level in LPCD | In case of any improvement / upgradation carried after commissioning then | Programme under which improvement / upgradation / carried out. | "Cost/ expenditure carried out on scheme (Rs. In Lacs)" | Present Service level in LPCD | Depth of T/well | Size of T/well | Year of Drilling | Original discharge at time of commissioning (in m3 per hour) | Present Discharge i.e. In 2017 (in m3 per hour) |  | Present Spring level in meters | Time of installation of new machinery | Capacity of machinery in BHP | Type of Inlet channel | Length of Inlet Channel in Kms | In case of piped, type of pipe | Capacity of SS Tank in cubic meter | Capacity of HL Tank in cubic meter | Capacity of CW Tank in cubic meter | Filtertion Units |  |  | Capacity of Raw water Motor (BHP) | Capacity of clear water Motor (BHP) | Nos. | Time of construction | Capacity in litres (in lacs) | C.T. | UGSR |  | Full supply level | Is OHSR in working condition | If no, then does it needs | In case of dismantling whether technical report from any institution has been received | AC |  |  | MS / DI / CI | GI | PVC |  |  | Total
[31 empty] | Type (Slow Sand / Rapid Sand / Pressure Filter / Compact Unit) | Nos | Capacity in cubic meter
1 |  | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 |  | 39 | 40 | 41 | 42 | 43 |  |  | 44 | 45 | 46 |  |  | 47 | 48
Zone: Central Zone; Circle: Muktsar Circle; District: Muktsar; Division: Muktsar, Div-1; Block: Muktsar
1 |  | 13136 |  | CA9232 | CA9232 | CANAL | SV | CA9232 | 1/31/01 12:00 AM | NRDWP | 40 | [13 empty] | Drain | 1.50 | RCC | 4169.00 | 83.00 | 83.00 | slow | 3 |  | 3.00 | 7.50 | 1 | 1/7/77 12:00 | 0.22 |  |  |  | 21.34 | N | Dismantlin | No
2 |  | 13136 |  | CA9232 | CA9232 | CANAL | SV | CA9232 | 1/31/01 12:00 AM | NRDWP | 40 | [13 empty] | Drain | 1.50 | RCC | 4169.00 | 83.00 | 83.00 | slow | 3 |  | 3.00 | 7.50 | 1 | 1/7/77 12:00 | 0.22 |  |  |  | 21.34 | N |  | No
3 |  | 13136 |  | CA9232 | CA9232 | CANAL | SV | CA9232 | 1/31/01 12:00 AM | NRDWP | 40 | [13 empty] | Drain | 1.50 | RCC | 4169.00 | 83.00 | 83.00 | slow | 3 |  | 3.00 | 7.50 | 1 | 1/7/77 12:00 | 0.22 |  |  |  | 21.34 | N | Dismantlin | No
4 |  | 13136 |  | CA9232 | CA9232 | CANAL | SV | CA9232 | 1/31/01 12:00 AM | NRDWP | 40 | [13 empty] | Drain | 1.50 | RCC | 4169.00 | 83.00 | 83.00 | slow | 3 |  | 3.00 | 7.50 | 1 | 1/7/77 12:00 | 0.22 |  |  |  | 21.34 | Y |  | No
Total |  | 4 |  | 4 | [20 empty] | 24: 6.00; Nos 30: 12; Capacity in cubic meter 34: 4
Zone: North Zone; Circle: Amritsar Circle; District: Amritsar; Division: Amritsar,Div-1; Block: Ajnala
5 |  | 2594 |  | TW1146 | TW1146 | TUBEWEL | SV | TW1146 | 1/1/10 12:00 AM | NRDWP QA | 40 |  |  |  |  | 11.00 | 1.00 | Oct-17 | 1 | 1 |  | 1.00 | 10/6/17 12:00 | 1.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 10/3/17 12:00; Capacity in cubic meter 36: 1.00 |  | 1 | Y |  |  | 1 |  |  | 1 | 1 | 1 |  |  | 4
Total |  | 1 |  | 1 | [41 empty] | 1 |  |  | 1 | 1 | 1 |  |  | 4 | bar: 23 to Capacity in cubic meter 38
Zone: North Zone; Circle: Amritsar Circle; District: Amritsar; Division: Amritsar,Div-2; Block: Rayya
6 |  | 2542 |  | TW19167 | TW19167 | TUBEWEL | SV | TW19167 | 3/31/16 12:00 AM | IBRD | 70 |  |  |  |  | 150.00 | 200.00 | Mar-16 | 40000 | 38000 |  | 30.00 | 12/30/13 12: | 15.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 3/31/16 12:00; Capacity in cubic meter 36: 0.50 |  | 20 | Y
7 |  | 2542 |  | TW19167 | TW19167 | TUBEWEL | SV | TW19167 | 3/31/16 12:00 AM | IBRD | 70 | [31 empty] | N
8 |  | 2542 |  | TW19167 | TW19167 | TUBEWEL | SV | TW19167 | 3/31/16 12:00 AM | IBRD | 70 |  |  |  |  | 150.00 | 200.00 | Mar-16 | 40000 | 38000 |  | 30.00 | 12/30/13 12: | 15.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 3/31/16 12:00; Capacity in cubic meter 36: 0.50 |  | 20 | Y |  |  | 0 |  |  | 0 | 0 | 3 |  |  | 3
9 |  | 2542 |  | TW19167 | TW19167 | TUBEWEL | SV | TW19167 | 3/31/16 12:00 AM | IBRD | 70 | [31 empty] | N |  |  | 0 |  |  | 0 | 0 | 3 |  |  | 3
Total |  | 4 |  | 4 | [20 empty] | Capacity in cubic meter 34: 2 | [5 empty] | 0 |  |  | 0 | 0 | 6 |  |  | 6
Zone: North Zone; Circle: Amritsar Circle; District: Amritsar; Division: Amritsar,Div-3; Block: Attari
10 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
Page 1 of |  |  | 7 | [17 empty] | Performa Report 1.2 | [19 empty] | 08/10/2017 16.18.49
Sr. No. |  | Village Name |  | Scheme Name | Present Status of Water Supply | [10 empty] | Present Status of Water Supply in 2017 | [29 empty] | Details of Distribution pipe line (In KM) | [8 empty] | % age of functional Distribution network as in 2017.
[16 empty] | In case of T/well based schemes details of latest tubewell drilled at site | [8 empty] | 23: In case of Canal based wss details of structures; Capacity in cubic meter 34: Details of OHSR's
[5 empty] | Water Supply Scheme under which habitaitons has been covered | Source of WSS | Type of scheme | WSS MIS ID. | Original Date of commissioning of WSS | Programme under which WSS was commissioned | Service level in LPCD | In case of any improvement / upgradation carried after commissioning then | Programme under which improvement / upgradation / carried out. | "Cost/ expenditure carried out on scheme (Rs. In Lacs)" | Present Service level in LPCD | Depth of T/well | Size of T/well | Year of Drilling | Original discharge at time of commissioning (in m3 per hour) | Present Discharge i.e. In 2017 (in m3 per hour) |  | Present Spring level in meters | Time of installation of new machinery | Capacity of machinery in BHP | Type of Inlet channel | Length of Inlet Channel in Kms | In case of piped, type of pipe | Capacity of SS Tank in cubic meter | Capacity of HL Tank in cubic meter | Capacity of CW Tank in cubic meter | Filtertion Units |  |  | Capacity of Raw water Motor (BHP) | Capacity of clear water Motor (BHP) | Nos. | Time of construction | Capacity in litres (in lacs) | C.T. | UGSR |  | Full supply level | Is OHSR in working condition | If no, then does it needs | In case of dismantling whether technical report from any institution has been received | AC |  |  | MS / DI / CI | GI | PVC |  |  | Total
[31 empty] | Type (Slow Sand / Rapid Sand / Pressure Filter / Compact Unit) | Nos | Capacity in cubic meter
1 |  | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 |  | 39 | 40 | 41 | 42 | 43 |  |  | 44 | 45 | 46 |  |  | 47 | 48
11 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
12 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
13 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
14 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
15 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
16 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
17 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
18 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
19 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
20 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
21 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
22 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
23 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
24 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
25 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
26 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
27 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
28 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
29 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
30 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
31 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
Page 2 of |  |  | 7 | [17 empty] | Performa Report 1.2 | [19 empty] | 08/10/2017 16.18.49
Sr. No. |  | Village Name |  | Scheme Name | Present Status of Water Supply | [10 empty] | Present Status of Water Supply in 2017 | [29 empty] | Details of Distribution pipe line (In KM) | [8 empty] | % age of functional Distribution network as in 2017.
[16 empty] | In case of T/well based schemes details of latest tubewell drilled at site | [8 empty] | 23: In case of Canal based wss details of structures; Capacity in cubic meter 34: Details of OHSR's
[5 empty] | Water Supply Scheme under which habitaitons has been covered | Source of WSS | Type of scheme | WSS MIS ID. | Original Date of commissioning of WSS | Programme under which WSS was commissioned | Service level in LPCD | In case of any improvement / upgradation carried after commissioning then | Programme under which improvement / upgradation / carried out. | "Cost/ expenditure carried out on scheme (Rs. In Lacs)" | Present Service level in LPCD | Depth of T/well | Size of T/well | Year of Drilling | Original discharge at time of commissioning (in m3 per hour) | Present Discharge i.e. In 2017 (in m3 per hour) |  | Present Spring level in meters | Time of installation of new machinery | Capacity of machinery in BHP | Type of Inlet channel | Length of Inlet Channel in Kms | In case of piped, type of pipe | Capacity of SS Tank in cubic meter | Capacity of HL Tank in cubic meter | Capacity of CW Tank in cubic meter | Filtertion Units |  |  | Capacity of Raw water Motor (BHP) | Capacity of clear water Motor (BHP) | Nos. | Time of construction | Capacity in litres (in lacs) | C.T. | UGSR |  | Full supply level | Is OHSR in working condition | If no, then does it needs | In case of dismantling whether technical report from any institution has been received | AC |  |  | MS / DI / CI | GI | PVC |  |  | Total
[31 empty] | Type (Slow Sand / Rapid Sand / Pressure Filter / Compact Unit) | Nos | Capacity in cubic meter
1 |  | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 |  | 39 | 40 | 41 | 42 | 43 |  |  | 44 | 45 | 46 |  |  | 47 | 48
32 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
33 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
34 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
35 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
36 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
37 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
38 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
39 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
40 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
41 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
42 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
43 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
44 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
45 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
46 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
47 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
48 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
49 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
50 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
51 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
52 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
Page 3 of |  |  | 7 | [17 empty] | Performa Report 1.2 | [19 empty] | 08/10/2017 16.18.49
Sr. No. |  | Village Name |  | Scheme Name | Present Status of Water Supply | [10 empty] | Present Status of Water Supply in 2017 | [29 empty] | Details of Distribution pipe line (In KM) | [8 empty] | % age of functional Distribution network as in 2017.
[16 empty] | In case of T/well based schemes details of latest tubewell drilled at site | [8 empty] | 23: In case of Canal based wss details of structures; Capacity in cubic meter 34: Details of OHSR's
[5 empty] | Water Supply Scheme under which habitaitons has been covered | Source of WSS | Type of scheme | WSS MIS ID. | Original Date of commissioning of WSS | Programme under which WSS was commissioned | Service level in LPCD | In case of any improvement / upgradation carried after commissioning then | Programme under which improvement / upgradation / carried out. | "Cost/ expenditure carried out on scheme (Rs. In Lacs)" | Present Service level in LPCD | Depth of T/well | Size of T/well | Year of Drilling | Original discharge at time of commissioning (in m3 per hour) | Present Discharge i.e. In 2017 (in m3 per hour) |  | Present Spring level in meters | Time of installation of new machinery | Capacity of machinery in BHP | Type of Inlet channel | Length of Inlet Channel in Kms | In case of piped, type of pipe | Capacity of SS Tank in cubic meter | Capacity of HL Tank in cubic meter | Capacity of CW Tank in cubic meter | Filtertion Units |  |  | Capacity of Raw water Motor (BHP) | Capacity of clear water Motor (BHP) | Nos. | Time of construction | Capacity in litres (in lacs) | C.T. | UGSR |  | Full supply level | Is OHSR in working condition | If no, then does it needs | In case of dismantling whether technical report from any institution has been received | AC |  |  | MS / DI / CI | GI | PVC |  |  | Total
[31 empty] | Type (Slow Sand / Rapid Sand / Pressure Filter / Compact Unit) | Nos | Capacity in cubic meter
1 |  | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 |  | 39 | 40 | 41 | 42 | 43 |  |  | 44 | 45 | 46 |  |  | 47 | 48
53 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
54 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
55 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
56 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
57 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
58 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
59 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
60 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
61 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
62 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
63 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
64 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
65 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
66 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
67 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
68 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
69 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
70 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
71 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
72 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
73 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
Page 4 of |  |  | 7 | [17 empty] | Performa Report 1.2 | [19 empty] | 08/10/2017 16.18.49
Sr. No. |  | Village Name |  | Scheme Name | Present Status of Water Supply | [10 empty] | Present Status of Water Supply in 2017 | [29 empty] | Details of Distribution pipe line (In KM) | [8 empty] | % age of functional Distribution network as in 2017.
[16 empty] | In case of T/well based schemes details of latest tubewell drilled at site | [8 empty] | 23: In case of Canal based wss details of structures; Capacity in cubic meter 34: Details of OHSR's
[5 empty] | Water Supply Scheme under which habitaitons has been covered | Source of WSS | Type of scheme | WSS MIS ID. | Original Date of commissioning of WSS | Programme under which WSS was commissioned | Service level in LPCD | In case of any improvement / upgradation carried after commissioning then | Programme under which improvement / upgradation / carried out. | "Cost/ expenditure carried out on scheme (Rs. In Lacs)" | Present Service level in LPCD | Depth of T/well | Size of T/well | Year of Drilling | Original discharge at time of commissioning (in m3 per hour) | Present Discharge i.e. In 2017 (in m3 per hour) |  | Present Spring level in meters | Time of installation of new machinery | Capacity of machinery in BHP | Type of Inlet channel | Length of Inlet Channel in Kms | In case of piped, type of pipe | Capacity of SS Tank in cubic meter | Capacity of HL Tank in cubic meter | Capacity of CW Tank in cubic meter | Filtertion Units |  |  | Capacity of Raw water Motor (BHP) | Capacity of clear water Motor (BHP) | Nos. | Time of construction | Capacity in litres (in lacs) | C.T. | UGSR |  | Full supply level | Is OHSR in working condition | If no, then does it needs | In case of dismantling whether technical report from any institution has been received | AC |  |  | MS / DI / CI | GI | PVC |  |  | Total
[31 empty] | Type (Slow Sand / Rapid Sand / Pressure Filter / Compact Unit) | Nos | Capacity in cubic meter
1 |  | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 |  | 39 | 40 | 41 | 42 | 43 |  |  | 44 | 45 | 46 |  |  | 47 | 48
74 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
75 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
76 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
77 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
78 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
79 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
80 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
81 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
82 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
83 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
84 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
85 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
86 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
87 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
88 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
89 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
90 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
91 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
92 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
93 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
94 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
Page 5 of |  |  | 7 | [17 empty] | Performa Report 1.2 | [19 empty] | 08/10/2017 16.18.49
Sr. No. |  | Village Name |  | Scheme Name | Present Status of Water Supply | [10 empty] | Present Status of Water Supply in 2017 | [29 empty] | Details of Distribution pipe line (In KM) | [8 empty] | % age of functional Distribution network as in 2017.
[16 empty] | In case of T/well based schemes details of latest tubewell drilled at site | [8 empty] | 23: In case of Canal based wss details of structures; Capacity in cubic meter 34: Details of OHSR's
[5 empty] | Water Supply Scheme under which habitaitons has been covered | Source of WSS | Type of scheme | WSS MIS ID. | Original Date of commissioning of WSS | Programme under which WSS was commissioned | Service level in LPCD | In case of any improvement / upgradation carried after commissioning then | Programme under which improvement / upgradation / carried out. | "Cost/ expenditure carried out on scheme (Rs. In Lacs)" | Present Service level in LPCD | Depth of T/well | Size of T/well | Year of Drilling | Original discharge at time of commissioning (in m3 per hour) | Present Discharge i.e. In 2017 (in m3 per hour) |  | Present Spring level in meters | Time of installation of new machinery | Capacity of machinery in BHP | Type of Inlet channel | Length of Inlet Channel in Kms | In case of piped, type of pipe | Capacity of SS Tank in cubic meter | Capacity of HL Tank in cubic meter | Capacity of CW Tank in cubic meter | Filtertion Units |  |  | Capacity of Raw water Motor (BHP) | Capacity of clear water Motor (BHP) | Nos. | Time of construction | Capacity in litres (in lacs) | C.T. | UGSR |  | Full supply level | Is OHSR in working condition | If no, then does it needs | In case of dismantling whether technical report from any institution has been received | AC |  |  | MS / DI / CI | GI | PVC |  |  | Total
[31 empty] | Type (Slow Sand / Rapid Sand / Pressure Filter / Compact Unit) | Nos | Capacity in cubic meter
1 |  | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 |  | 39 | 40 | 41 | 42 | 43 |  |  | 44 | 45 | 46 |  |  | 47 | 48
95 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
96 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
97 |  | 3090 |  | TW1209 | TW1209 | TUBEWEL | SV | TW1209 | 12/1/08 12:00 AM | RIDF XI | 70 | 2017-10-02 |  | 100.00 |  | 1.00 | 2.00 | Oct-17 | 3 | 4 |  | 5.00 | 10/5/17 12:00 | 6.00 | Capacity in cubic meter 34: 7; Capacity in cubic meter 35: 10/5/17 12:00; Capacity in cubic meter 36: 8.00 |  | 9 | N | Dismantlin | No | 6 |  |  | 6 | 6 | 6 |  |  | 24
Total |  | 88 |  | 88 | [9 empty] | 8800.00 | [10 empty] | Capacity in cubic meter 34: 616 | [5 empty] | 528 |  |  | 528 | 528 | 528 |  |  | 2112
Zone: North Zone; Circle: Amritsar Circle; District: Tarntaran; Division: Tarn Taran; Block: Tarn Taran
98 |  | 3344 |  | TW19152 | TW19152 | TUBEWEL | SV | TW19152 | 9/30/16 12:00 AM | IBRD | 70 |  |  |  |  | 150.00 | 200.00 | Mar-15 | 40 | 40 |  | 20.00 | 1/3/16 12:00 | 10.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 3/31/16 12:00; Capacity in cubic meter 36: 0.75 |  | 20 | Y
99 |  | 3344 |  | TW19152 | TW19152 | TUBEWEL | SV | TW19152 | 9/30/16 12:00 AM | IBRD | 70 |  |  |  |  | 150.00 | 200.00 | Mar-15 | 40 | 40 |  | 20.00 | 1/3/16 12:00 | 10.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 3/31/16 12:00; Capacity in cubic meter 36: 0.75 |  | 20 | Y
100 |  | 3344 |  | TW19152 | TW19152 | TUBEWEL | SV | TW19152 | 9/30/16 12:00 AM | IBRD | 70 |  |  |  |  | 150.00 | 200.00 | Mar-15 | 40 | 40 |  | 20.00 | 1/3/16 12:00 | 10.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 3/31/16 12:00; Capacity in cubic meter 36: 0.75 |  | 20 | Y
101 |  | 3344 |  | TW19152 | TW19152 | TUBEWEL | SV | TW19152 | 9/30/16 12:00 AM | IBRD | 70 |  |  |  |  | 150.00 | 200.00 | Mar-15 | 40 | 40 |  | 20.00 | 1/3/16 12:00 | 10.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 3/31/16 12:00; Capacity in cubic meter 36: 0.75 |  | 20 | Y
Total |  | 4 |  | 4 | [20 empty] | Capacity in cubic meter 34: 4
Zone: North Zone; Circle: Hoshiarpur Circle; District: SBS Nagar; Division: SBS Nagar, Div; Block: Nawan Shahar
102 |  | 6594 |  | TW10467 | TW10467 | TUBEWEL | SV | TW10467 | 12/1/93 12:00 AM | MNP | 40 |  |  |  |  | 150.00 | 300.00 | Dec-93 | 54000 | 35000 |  | 30.00 | 12/1/93 12:00 | 15.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 9/1/93 12:00; Capacity in cubic meter 36: 1.50 |  | 27.43 | Y |  |  | 1455 |  |  | 0 | 0 | 2169 |  |  | 3624
Total |  | 1 |  | 1 | [41 empty] | 1455 |  |  | 0 | 0 | 2169 |  |  | 3624 | bar: 23 to Capacity in cubic meter 38
Zone: South Zone; Circle: Chandigarh Circle; District: SAS Nagar; Division: SAS Nagar, Div-3; Block: Dera Bassi
103 |  | 7586 |  | TW2582 | TW2582 | TUBEWEL | SV | TW2582 | 2/1/10 12:00 AM | IDA | 70 |  |  | 0.46 |  | 300.00 | 200.00 | Feb-10 | 40000 | 40000 |  | 90.00 | 2/1/10 12:00 | 20.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 2/1/10 12:00; Capacity in cubic meter 36: 75000.00 |  | 22 | Y
104 |  | 7586 |  | TW2582 | TW2582 | TUBEWEL | SV | TW2582 | 2/1/10 12:00 AM | IDA | 70 | 2010-02-01 |  | 0.46 |  | 300.00 | 200.00 | Feb-10 | 40000 | 40000 |  | 90.00 | 2/1/10 12:00 | 20.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 2/1/10 12:00; Capacity in cubic meter 36: 75000.00 |  | 22 | Y
105 |  | 7586 |  | TW2582 | TW2582 | TUBEWEL | SV | TW2582 | 2/1/10 12:00 AM | IDA | 70 | [31 empty] | N
Total |  | 3 |  | 3 | [9 empty] | 0.92 | [10 empty] | Capacity in cubic meter 34: 2
Zone: South Zone; Circle: Ludhiana Circle; District: Ludhiana; Division: Ludhiana, Div-3; Block: Sidhwan Bet
106 |  | 8973 |  | TW16629 | TW16629 | TUBEWEL | SV | TW16629 | 3/31/15 12:00 AM | NRDWP SWAP | 70 |  |  |  |  | 150.00 | 150.00 | Jan-16 | 40 | 30 |  | 15.00 | 12/31/16 12: | 5.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 11/30/14 12:00; Capacity in cubic meter 36: 0.25 |  | 18 | Y |  |  | 0 |  |  | 0 | 0 | 3 |  |  | 3
Total |  | 1 |  | 1 | [41 empty] | 0 |  |  | 0 | 0 | 3 |  |  | 3 | bar: 23 to Capacity in cubic meter 38
Page 6 of |  |  | 7 | [17 empty] | Performa Report 1.2 | [19 empty] | 08/10/2017 16.18.49
Sr. No. |  | Village Name |  | Scheme Name | Present Status of Water Supply | [10 empty] | Present Status of Water Supply in 2017 | [29 empty] | Details of Distribution pipe line (In KM) | [8 empty] | % age of functional Distribution network as in 2017.
[16 empty] | In case of T/well based schemes details of latest tubewell drilled at site | [8 empty] | 23: In case of Canal based wss details of structures; Capacity in cubic meter 34: Details of OHSR's
[5 empty] | Water Supply Scheme under which habitaitons has been covered | Source of WSS | Type of scheme | WSS MIS ID. | Original Date of commissioning of WSS | Programme under which WSS was commissioned | Service level in LPCD | In case of any improvement / upgradation carried after commissioning then | Programme under which improvement / upgradation / carried out. | "Cost/ expenditure carried out on scheme (Rs. In Lacs)" | Present Service level in LPCD | Depth of T/well | Size of T/well | Year of Drilling | Original discharge at time of commissioning (in m3 per hour) | Present Discharge i.e. In 2017 (in m3 per hour) |  | Present Spring level in meters | Time of installation of new machinery | Capacity of machinery in BHP | Type of Inlet channel | Length of Inlet Channel in Kms | In case of piped, type of pipe | Capacity of SS Tank in cubic meter | Capacity of HL Tank in cubic meter | Capacity of CW Tank in cubic meter | Filtertion Units |  |  | Capacity of Raw water Motor (BHP) | Capacity of clear water Motor (BHP) | Nos. | Time of construction | Capacity in litres (in lacs) | C.T. | UGSR |  | Full supply level | Is OHSR in working condition | If no, then does it needs | In case of dismantling whether technical report from any institution has been received | AC |  |  | MS / DI / CI | GI | PVC |  |  | Total
[31 empty] | Type (Slow Sand / Rapid Sand / Pressure Filter / Compact Unit) | Nos | Capacity in cubic meter
1 |  | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 |  | 39 | 40 | 41 | 42 | 43 |  |  | 44 | 45 | 46 |  |  | 47 | 48
Zone: South Zone; Circle: Sangrur Circle; District: Sangrur; Division: Sangrur; Block: Sangrur
107 |  | 11123 |  | TW3126 | TW3126 | TUBEWEL | SV | TW3126 | 9/1/10 12:00 AM | NRDWP SWAP | 70 |  |  |  |  | 200.00 | 150.00 | Jan-10 | 50000 | 70000 |  | 26.00 | 1/4/17 12:00 | 20.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 8/31/16 12:00; Capacity in cubic meter 36: 0.50 |  | 40 | Y |  |  | 0 |  |  | 0 | 0 | 4560 |  |  | 4560
108 |  | 11123 |  | TW3126 | TW3126 | TUBEWEL | SV | TW3126 | 9/1/10 12:00 AM | NRDWP SWAP | 70 |  |  |  |  | 200.00 | 150.00 | Jan-10 | 50000 | 70000 |  | 26.00 | 1/4/17 12:00 | 20.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 8/31/16 12:00; Capacity in cubic meter 36: 0.50 |  | 40 | Y |  |  | 0 |  |  | 0 | 0 | 4560 |  |  | 4560
109 |  | 11123 |  | TW3126 | TW3126 | TUBEWEL | SV | TW3126 | 9/1/10 12:00 AM | NRDWP SWAP | 70 |  |  |  |  | 200.00 | 150.00 | Jan-10 | 50000 | 70000 |  | 26.00 | 1/4/17 12:00 | 20.00 | Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 8/31/16 12:00; Capacity in cubic meter 36: 0.50 |  | 20 | Y |  |  | 0 |  |  | 0 | 0 | 4560 |  |  | 4560
Total |  | 3 |  | 3 | [20 empty] | Capacity in cubic meter 34: 3 | [5 empty] | 0 |  |  | 0 | 0 | 13680 |  |  | 13680
Zone: null; Circle: null; District: null; Division: null; Block: null
110 |  |  |  | TW12259 | TW12259 | TUBEWEL | MV | TW12259 | 4/30/06 12:00 AM | NABARD-NON | 70 |  |  |  |  | 200.00 | 250.00 | Apr-08 | 40 | 40 |  | 110.00 | 7/3/08 12:00 | 20.00 | 23: 0; 24: 0.00; 25: 0; 26: 0.00; Capacity in cubic meter 34: 1; Capacity in cubic meter 35: 7/3/08 12:00; Capacity in cubic meter 36: 2.50 |  | 28 | Y |  |  | 14515 |  |  | 0 | 375 | 0 |  |  | 14890
Total |  | 1 |  | 1 | [20 empty] | 24: 0.00; Capacity in cubic meter 34: 1 | [5 empty] | 14515 |  |  | 0 | 375 | 0 |  |  | 14890
Grand Total |  | 110 |  | 110 | [9 empty] | 8800.92 | [10 empty] | 24: 6.00; Nos 30: 12; Capacity in cubic meter 34: 635 | [5 empty] | 16499 |  |  | 529 | 904 | 16387 |  |  | 34319
Version: 1.0
Page 7 of |  |  | 7 | [17 empty] | Performa Report 1.2 | [19 empty] | 08/10/2017 16.18.49